## Requirements Inventory
Goal ID | SMART Goal | Requirement ID | Requirement Statement
G1 | Enable teachers to create classes and group students into teams by the end of Sprint 1, supporting full class and team setup before evaluation activities begin. | REQ-101 | The system shall allow teachers to create a new class with details including name, section, school year, and description.
|  | REQ-102 | The system shall display all created classes in the teacher dashboard.
|  | REQ-103 | The system shall allow teachers to add, edit, and remove students within a selected class, with validation before saving.
|  | REQ-104 | The system shall display the student list within each class, organized by class.
|  | REQ-105 | The system shall enable teachers to create teams under a specific class and assign students to those teams.
|  | REQ-106 | The system shall prevent duplicate student assignments across multiple teams within the same class.
|  | REQ-107 | The system shall allow teachers to link an adviser to a specific team and validate adviser availability within the class.
|  | REQ-108 | The system shall display all adviser–team relationships in the teacher dashboard.
|  | REQ-109 | The system shall integrate with the Google Forms API to fetch available questionnaires and allow teachers to assign specific questionnaires to teams.
|  | REQ-110 | The system shall ensure that assigned questionnaires appear in the adviser dashboard for scoring purposes.
G2 | Allow advisers to score their assigned teams using custom questionnaires via the Google Forms API within 4 weeks of development, ensuring all evaluations are submitted and tracked online. | REQ-201 | The system shall display to each adviser all classes where they are assigned to at least one team, with navigation to view class details.
|  | REQ-202 | The system shall show the list of teams assigned to the adviser under each class.
|  | REQ-203 | The system shall display the designated questionnaire for each team and allow advisers to submit scores per questionnaire item.
|  | REQ-204 | The system shall validate scoring input to prevent incomplete or missing submissions before saving to the database.
|  | REQ-205 | The system shall show advisers which teams they have already scored and which teams still require evaluation.
|  | REQ-206 | The system shall allow advisers to update previously submitted scores if the teacher has granted permission for revision.
G3 | Begin implementing the reporting and AI summarization features by Sprint 3 and continue refining throughout remaining sprints, enabling teachers to generate automated performance summaries and export reports. | REQ-301 | The system shall calculate team performance rankings based on total adviser scores and identify the best-performing and lowest-performing teams.
|  | REQ-302 | The system shall display team performance rankings in a clear list or table format on the teacher reporting page.
|  | REQ-303 | The system shall use AI (Google Gemini API) to generate summarized reports of team performance, including insights into strengths and weaknesses.
|  | REQ-304 | The system shall automatically update AI-generated summaries when new adviser scores are submitted.
|  | REQ-305 | The system shall provide a dedicated reporting page accessible from the teacher dashboard showing rankings, AI summaries, charts, and data visualizations.
|  | REQ-306 | The system shall allow teachers to export evaluation reports in PDF and CSV formats.
G4 | Implement secure logins and role-based access control throughout all development sprints, ensuring data privacy compliance with the Data Privacy Act of 2012 before system go-live. | REQ-401 | The system shall implement secure local authentication for teachers and advisers using email/username and password, with passwords hashed using industry-standard algorithms.
|  | REQ-402 | The system shall maintain secure session tokens (JWT or server sessions) for all authenticated users.
|  | REQ-403 | The system shall allow teachers to link or unlink a Google account via OAuth for accessing Google Drive and Google Forms on their behalf, without using Google OAuth as the primary login method.
|  | REQ-404 | The system shall request only the minimum required Google OAuth scopes (Google Forms and Drive access) and store tokens securely associated with the teacher account.
|  | REQ-405 | The system shall restrict teacher functions (class creation, team formation, questionnaire assignment, report viewing) from adviser-level users and vice versa.
|  | REQ-406 | The system shall prevent users from accessing dashboards or data outside their assigned role.
|  | REQ-407 | The system shall implement server-side input validation and sanitization to prevent SQL injection and XSS attacks.
|  | REQ-408 | The system shall secure all API communications using HTTPS and protect OAuth tokens and sensitive data using encryption at rest and in transit.
G5 | Improve the fairness and consistency of student peer evaluations by 30% within the first semester after deployment by implementing a structured peer evaluation system with standardized rubrics, required rating fields, and automatic scoring rules. | REQ-501 | The system shall provide students with a peer evaluation form containing required rating fields based on standardized rubrics, preventing submission if any field is incomplete.
|  | REQ-502 | The system shall enforce standardized rubric criteria uniformly across all peer evaluations within the same class or activity.
|  | REQ-503 | The system shall prevent duplicate peer evaluation submissions by the same student for the same evaluatee within a single evaluation period.
|  | REQ-504 | The system shall prevent late submissions after the teacher-defined evaluation deadline has passed.
|  | REQ-505 | The system shall automatically compute the total evaluation score per evaluatee based on all submitted peer ratings.
|  | REQ-506 | The system shall store all completed evaluation records in the database and generate confirmation messages upon successful submission.
|  | REQ-507 | The system shall allow teachers to view, filter, and download peer evaluation summaries per student.
|  | REQ-508 | The system shall submit evaluation forms within ≤ 1 second under normal operating conditions and display the interface in a mobile-responsive format.
G6 | Achieve at least 70% user satisfaction in feedback clarity and usefulness by generating automated AI-powered summaries and categorized insights within three months of system launch. | REQ-601 | The system shall collect all peer-submitted text comments for a single student and pass them to the AI/NLP module for processing.
|  | REQ-602 | The system shall use NLP techniques to summarize peer feedback comments into a concise, student-readable summary highlighting key points.
|  | REQ-603 | The system shall categorize peer feedback comments into three categories: strengths, weaknesses, and suggestions for improvement.
|  | REQ-604 | The system shall detect and remove redundant or repetitive peer feedback comments before generating the final summary.
|  | REQ-605 | The system shall generate each AI summary within ≤ 2 seconds of a summarization request and update automatically when new peer evaluations are submitted.
|  | REQ-606 | The system shall present the generated summary report on a dedicated student-readable insights page, without exposing raw peer data to unauthorized users.
|  | REQ-607 | The system shall write all AI-generated summaries in clear, readable language appropriate for the student audience.
G7 | Increase clarity and usefulness of evaluation results for 80% of students and teachers by providing AI-enhanced dashboards with real-time analytics and visual reports within the first semester of use. | REQ-701 | The system shall provide a student dashboard displaying their peer evaluation history, AI-generated feedback summary, and score trends across multiple evaluation periods.
|  | REQ-702 | The system shall provide a teacher dashboard displaying class-level analytics including individual student scores, participation rates, and overall class performance.
|  | REQ-703 | The system shall aggregate AI results, evaluation scores, and system analytics in real time and render them as graphs, charts, and summary tables.
|  | REQ-704 | The system shall apply role-based views so that students see only their own evaluation data and teachers see class-wide data.
|  | REQ-705 | The system shall load all dashboard pages within ≤ 1.5 seconds under normal operating conditions.
|  | REQ-706 | The system shall maintain a mobile-responsive UI built with React.js and achieve ≥ 99% uptime via cloud hosting on Google Cloud.
G8 | Ensure 100% compliance with the Philippine Data Privacy Act and achieve secure access for all users through Google OAuth2 authentication and encrypted data handling before the system's initial deployment. | REQ-801 | The system shall implement Google OAuth2 authentication for all users (students, teachers, admin) and generate JWT tokens upon successful login.
|  | REQ-802 | The system shall verify the role of each authenticated user (student, teacher, admin) and restrict access to pages and functions based on assigned role.
|  | REQ-803 | The system shall encrypt all data at rest and in transit using SSL/TLS, achieving an authentication success rate of ≥ 99%.
|  | REQ-804 | The system shall ensure full compliance with the Philippine Data Privacy Act, including secure data storage, restricted access, and no unauthorized exposure of personal evaluation data.
|  | REQ-805 | The system shall achieve ≥ 80% student satisfaction in post-deployment surveys, ≥ 25% reduction in teacher workload, and ≥ 30% improvement in evaluation fairness within the first semester.

## Traceability Matrix
Req ID | Requirement Statement | Goal ID | Module | Priority | Type | Acceptance Criteria | Verification Method | Status
REQ-101 | Create class with name, section, school year, description | G1 | Class & Team Mgmt | High | Functional | Class saved and visible in dashboard; all fields validated | UAT + Functional Test | Planned
REQ-102 | Display all classes in teacher dashboard | G1 | Class & Team Mgmt | High | Functional | All created classes appear on teacher home screen | UAT | Planned
REQ-103 | Add/edit/remove students with validation | G1 | Class & Team Mgmt | High | Functional | Invalid data rejected; changes reflected immediately | Functional Test | Planned
REQ-104 | Display student list per class | G1 | Class & Team Mgmt | Medium | Functional | Students listed under correct class only | UAT | Planned
REQ-105 | Create teams and assign students | G1 | Class & Team Mgmt | High | Functional | Teams saved under class; students assigned correctly | Functional Test | Planned
REQ-106 | Prevent duplicate student-team assignments | G1 | Class & Team Mgmt | High | Functional | System blocks duplicate assignment and shows error message | Functional Test | Planned
REQ-107 | Link adviser to team; validate adviser availability | G1 | Class & Team Mgmt | High | Functional | Adviser linked successfully; duplicate assignments blocked | Functional Test | Planned
REQ-108 | Display adviser–team relationships in dashboard | G1 | Class & Team Mgmt | Medium | Functional | Relationships visible in teacher dashboard table | UAT | Planned
REQ-109 | Google Forms API integration for questionnaire fetch & assign | G1 | Class & Team Mgmt | High | Integration | Forms fetched from Google; assigned forms appear in adviser view | Integration Test | Planned
REQ-110 | Assigned questionnaires appear in adviser dashboard | G1 | Class & Team Mgmt | High | Functional | Adviser sees correct form immediately after teacher assigns it | UAT | Planned
REQ-201 | Adviser dashboard shows assigned classes | G2 | Adviser Evaluation | High | Functional | Only classes with adviser's teams are shown | UAT | Planned
REQ-202 | Show list of adviser's teams per class | G2 | Adviser Evaluation | High | Functional | Correct teams displayed under each class | UAT | Planned
REQ-203 | Display questionnaire and allow score submission per item | G2 | Adviser Evaluation | High | Functional | Adviser can input and submit scores for all rubric items | Functional Test + UAT | Planned
REQ-204 | Validate scoring input; prevent incomplete submission | G2 | Adviser Evaluation | High | Functional | System blocks submission if any required field is empty | Functional Test | Planned
REQ-205 | Track which teams are scored vs. pending | G2 | Adviser Evaluation | Medium | Functional | Scored/pending status accurate per adviser view | UAT | Planned
REQ-206 | Allow score revision if teacher permits | G2 | Adviser Evaluation | Medium | Functional | Edit option appears only when teacher has enabled revision | Functional Test | Planned
REQ-301 | Calculate and rank team performance from adviser scores | G3 | Reporting & AI | High | Functional | Rankings computed correctly; tied scores handled consistently | Unit Test + UAT | Planned
REQ-302 | Display rankings in list/table on reporting page | G3 | Reporting & AI | High | Functional | Ranked table renders correctly with all teams listed | UAT | Planned
REQ-303 | AI (Gemini API) generates team performance summary | G3 | Reporting & AI | High | AI / Functional | AI summary includes strengths, weaknesses; readable language | AI Accuracy Test + UAT | Planned
REQ-304 | Auto-update AI summaries on new score submission | G3 | Reporting & AI | Medium | AI / Functional | Summary changes within 5 s of new score being saved | Integration Test | Planned
REQ-305 | Reporting page with rankings, summaries, charts | G3 | Reporting & AI | High | Functional | Page accessible from dashboard; all widgets render correctly | UAT | Planned
REQ-306 | Export reports as PDF and CSV | G3 | Reporting & AI | Medium | Functional | Both formats download correctly with accurate data | Output Verification | Planned
REQ-401 | Local auth with hashed passwords | G4 | Auth & Security | Critical | Security | Passwords stored as bcrypt hash; login works with correct credentials | Security Test | Planned
REQ-402 | Secure JWT/session tokens | G4 | Auth & Security | Critical | Security | Token expires correctly; invalid tokens rejected | Penetration Test | Planned
REQ-403 | Google OAuth account linking for Google Drive/Forms | G4 | Auth & Security | High | Integration | Teacher can link/unlink Google account; no Google login as primary auth | Integration Test | Planned
REQ-404 | Minimum Google OAuth scopes; secure token storage | G4 | Auth & Security | High | Security | Only Forms/Drive scopes requested; tokens encrypted in DB | Security Audit | Planned
REQ-405 | RBAC: restrict teacher vs. adviser functions | G4 | Auth & Security | Critical | Security | Advisers cannot access teacher-only pages and vice versa | Access Control Test | Planned
REQ-406 | Block cross-role dashboard access | G4 | Auth & Security | Critical | Security | Unauthorized route access returns 403 error | Penetration Test | Planned
REQ-407 | Server-side input validation and sanitization | G4 | Auth & Security | High | Security | SQL injection and XSS attempts blocked; malformed input rejected | Security Test | Planned
REQ-408 | HTTPS for all communications; encryption at rest/transit | G4 | Auth & Security | Critical | Security | All traffic over HTTPS; DB fields encrypted; verified by audit | Security Audit + Pen Test | Planned
REQ-501 | Peer evaluation form with required rubric rating fields | G5 | Peer Evaluation Mgmt | High | Functional | Incomplete form blocked from submission; all rubric fields required | Functional Test + UAT | Planned
REQ-502 | Enforce standardized rubrics across all evaluations | G5 | Peer Evaluation Mgmt | High | Functional | Same rubric applied to all peers in a class activity | UAT | Planned
REQ-503 | Prevent duplicate peer evaluation submissions | G5 | Peer Evaluation Mgmt | High | Functional | Second submission attempt blocked; first submission preserved | Functional Test | Planned
REQ-504 | Prevent late submissions after deadline | G5 | Peer Evaluation Mgmt | Medium | Functional | Form disabled after deadline; late attempts show clear error message | Functional Test | Planned
REQ-505 | Auto-compute total score per evaluatee | G5 | Peer Evaluation Mgmt | High | Functional | Total score correctly aggregates all rubric item ratings | Unit Test | Planned
REQ-506 | Store records and confirm successful submission | G5 | Peer Evaluation Mgmt | High | Functional | Record saved in DB; confirmation message displayed to student | Integration Test | Planned
REQ-507 | Teacher can view, filter, and download peer eval summaries | G5 | Peer Evaluation Mgmt | High | Functional | Teacher sees all students' summaries; filter and download work | UAT | Planned
REQ-508 | Form submission ≤ 1 s; mobile-responsive UI | G5 | Peer Evaluation Mgmt | High | Non-Functional | p95 submission ≤ 1 s at expected load; layout correct on mobile | Performance + Responsive Test | Planned
REQ-601 | Collect all peer text comments per student for NLP | G6 | AI Summarization | High | Functional | All submitted comments for a student fed to AI module | Integration Test | Planned
REQ-602 | NLP summarization of peer feedback comments | G6 | AI Summarization | High | AI / Functional | Summary concise, accurate, and in readable English | AI Accuracy Test | Planned
REQ-603 | Categorize comments: strengths, weaknesses, suggestions | G6 | AI Summarization | High | AI / Functional | Each comment correctly categorized; all 3 categories always present | AI Accuracy Test + UAT | Planned
REQ-604 | Detect and remove redundant comments before summarizing | G6 | AI Summarization | Medium | AI / Functional | Duplicate/near-duplicate comments collapsed; unique insights preserved | AI Accuracy Test | Planned
REQ-605 | Summary generated ≤ 2 s; auto-updates on new submission | G6 | AI Summarization | High | Non-Functional | p95 generation ≤ 2 s; summary refreshes after new eval saved | Performance Test | Planned
REQ-606 | Student-readable insights page; no raw data exposure | G6 | AI Summarization | High | Security / Functional | Students see only their own summary; raw peer data not accessible | Security Test + UAT | Planned
REQ-607 | AI summaries written in clear, student-appropriate language | G6 | AI Summarization | Medium | Usability | 80% of pilot students rate summary clarity ≥ 4/5 in UAT survey | Usability Test | Planned
REQ-701 | Student dashboard with eval history, AI summary, score trends | G7 | Dashboard | High | Functional | Student sees own history and summary; trend chart accurate | UAT | Planned
REQ-702 | Teacher dashboard with class-level analytics | G7 | Dashboard | High | Functional | Teacher sees all students' scores, participation, class averages | UAT | Planned
REQ-703 | Real-time aggregation of AI results and scores into charts | G7 | Dashboard | High | Functional | Charts update within 5 s of new data; graphs render correctly | Integration + UAT | Planned
REQ-704 | Role-based views: students see own data only | G7 | Dashboard | Critical | Security | Students cannot view other students' data; verified by access test | Access Control Test | Planned
REQ-705 | Dashboard loads ≤ 1.5 s under normal conditions | G7 | Dashboard | High | Non-Functional | p95 load ≤ 1.5 s at expected concurrent users | Performance Test | Planned
REQ-706 | Mobile-responsive React UI; ≥ 99% uptime on Google Cloud | G7 | Dashboard | High | Non-Functional | Responsive on mobile and tablet; uptime SLA met over 30-day period | Responsive Test + Uptime Monitor | Planned
REQ-801 | Google OAuth2 authentication + JWT token generation | G8 | Auth, Security & Privacy | Critical | Security | OAuth2 login succeeds; JWT generated and used for all subsequent requests | Security Test | Planned
REQ-802 | Role verification and access restriction per role | G8 | Auth, Security & Privacy | Critical | Security | Students, teachers, and admins restricted to respective pages only | Access Control Test | Planned
REQ-803 | SSL/TLS encryption; ≥ 99% auth success rate | G8 | Auth, Security & Privacy | Critical | Security | All traffic over HTTPS; auth failure rate < 1% in load test | Penetration Test + Load Test | Planned
REQ-804 | Full Philippine Data Privacy Act compliance | G8 | Auth, Security & Privacy | Critical | Compliance | No PII exposed without consent; audit log maintained; DPA checklist passed | Compliance Audit | Planned
REQ-805 | ≥ 80% student satisfaction; ≥ 25% teacher workload reduction; ≥ 30% fairness improvement | G8 | Auth, Security & Privacy | High | KPI | Post-deployment survey and comparative analysis confirm all three metrics | Survey + Comparative Study | Planned

## Legend & Glossary
Term / Code | Value / Color | Description
PROJECT A |  | Adviser Evaluation (Using Google API and AI) — CIT-U ¦ Team: Abdiano, Cortes, Ricablanca, Pael, Rivera ¦ Adviser: Cheryl B. Pantaleon
PROJECT B |  | APEER: AI Self and Peer Evaluation System — CIT-U ¦ Team: Bajamunde, Magpatoc, Queddeng, Rigodon, Tabungar ¦ Adviser: Ralph P. Laviste
Goal ID G1–G4 | Navy | Goals from Project A (Adviser Evaluation System)
Goal ID G5–G8 | Navy | Goals from Project B (APEER – AI Peer Evaluation)
SMART Goal |  | Specific, Measurable, Achievable, Relevant, Time-bound objective tied to a module.
Req ID |  | Unique requirement identifier: REQ-XYZ. First digit = Goal Group (1=G1, 5=G5, etc.)
Priority: Critical | RED | Must be implemented before system go-live; failure blocks launch.
Priority: High | ORANGE | Core functionality; must be in initial release.
Priority: Medium | GREEN | Important; may be deferred to a follow-up sprint if necessary.
Priority: Low | GREY | Nice-to-have; scheduled for future release.
Type: Functional |  | Describes what the system does — a specific behavior or feature.
Type: Non-Functional |  | Describes how the system performs — speed, uptime, scalability, UX.
Type: AI / Functional |  | Requirement involving AI/NLP model outputs or accuracy thresholds.
Type: Security |  | Authentication, authorization, encryption, or data-protection requirement.
Type: Integration |  | Requirement involving a third-party API (Google Forms, Google OAuth, Gemini).
Type: Compliance |  | Legal or regulatory requirement (Data Privacy Act, FERPA).
Type: KPI |  | Success metric tied to post-deployment measurement.
Status: Planned | BLUE | Documented; development not yet started.
Status: In Progress | ORANGE | Actively being developed or tested.
Status: Done | GREEN | Implemented and verified.
Google Forms API |  | Used in Project A to fetch and assign questionnaires to teams.
Google Gemini API |  | AI model used in Project A for generating team performance summaries.
NLP |  | Natural Language Processing — used in Project B to summarize and categorize peer feedback.
JWT |  | JSON Web Token — used for secure session management in both systems.
OAuth2 |  | Google OAuth2 — used in Project A for account linking; primary auth in Project B.
RBAC |  | Role-Based Access Control — restricts features by user role (Teacher, Adviser, Student).
Philippine Data Privacy Act |  | RA 10173 — governs personal data protection in the Philippines; applies to Project B.
UAT |  | User Acceptance Testing — validates usability with real teachers, advisers, and students.
Spring Boot |  | Java backend framework used in both Project A and Project B.
React.js |  | Frontend JavaScript framework used in both projects for responsive UI.
Google Cloud |  | Cloud hosting platform used for deployment and scalability in both projects.